## 2020-03-09
Module Name | Issue Description
General Design | For the screen where information is added on left side, button should be placed immediate after end of the input field
Overall Font size should be small
Dashboard | Footer Image Change
Document Advanced Search | Default date need to be changed at current data in "From Date" field
Update Profile | Menu does not appear while filling up personal data
File upload does not show included file name
Update button is not working
Update Password | Is not working
System Related Menu | Now is appearing from clicking on Super Admin button. But it should be somewhere else
User Role | When Updated, order of role changes in screen
Need to set the "Submit Role" button immediate after last field
Location Hierarchies | When Updated, order of Hierarchies changes in screen
Need to set the "Submit Hierarchey" button immediate after last field
Approval Level Information | Button name need to change from "Submit Project" to "Submit Approval"
System Config Menu | Depreciation Methods need to move from "System Config" to "Settings" Menu
Setting Menu | Setting menu label need to be changed to "Settings"
Project Information | While Updating Project Information, Showing error
Location Information | Location Type -----> Type
Parent ID should show Parent Name in Location List
Register User | Register button is overlapping with bottom field
Assign Role | No menu assignment
AMC Type | In AMC Type List window "Loading" word must be replaced
AMC Type master entry is not saving
Cmplaint Sub-Category Information | Status ???
User Complaints | Solution colum is there but No input for Solution
Asset Management - > My Delivery | Data Table CSS need to change
Button is not working
Asset Management - > Delivery Received | Data Table CSS need to change
Button is not working
Challan Add | Labal Add Challan Info First ---> Challan Info
Choose File, Challan Details, Comment should not be manadatory field
Asset Registration from New Challan Entry | Asset Category, Sub Category, Product, All Cost Information, Quantity and Serial No are mandatory
Asset Registration Title is absent
Warranty will be in month
Usefull life will be in month
Plus button for AMC type
Asset Registration from Challan List | All Plus button is not working

## Sheet2
Vendor's Details need to be added